## Gantt Chart
	[Project Name]				65%
	[Company]
	[Project Manager]		Mittwoch, 20. Mai 2015

										19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41					42					43
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Mai-15					Jun-15					Jul-15					Aug-15					Sep-15					Okt-15					Nov-15
			05-Mai-2015	21	02-Jun-2015	65%	29			05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01

	Template Neu	[name]	20-Mai-2015	1	20-Mai-2015	0%	1	0	1
	neu		20-Mai-2015	1	20-Mai-2015	0%	1	0	1

	Dummy 2. Bauabschnitt FTTH "Am Weinberg II", Wöllstadt	[name]	05-Mai-2015	21	02-Jun-2015	0%	29	0	3
	Eingabe in Plural NBG		05-Mai-2015	2	06-Mai-2015	0%	2	0	2
	Struktuplanung für Dummy-Bauabschnitt		02-Jun-2015	1	02-Jun-2015	0%	1	0	1

	Grundhafte Erneuerung Klein Welzheimer Straße, Seligenstadt	[name]	19-Mai-2015	1	19-Mai-2015	0%	1	0	1
	Rückmeldung	W00000157461290	19-Mai-2015	1	19-Mai-2015	0%	1	0	1

	Vollbeschaltung Kvz, 6004/1, Münzenberg	[name]	19-Mai-2015	1	19-Mai-2015	62%	1	1	1
	Strukturplanung Kvz A4	W00000160771574	19-Mai-2015	1	19-Mai-2015	23%	1	0	1
	Strukturplanung Kvz A1, A3	W00000155336752	19-Mai-2015	1	19-Mai-2015	100%	1	1	0

	Ermittlung Bauträger mit Projekten > 100WE	[name]	19-Mai-2015	1	19-Mai-2015	100%	1	0	0
	Rückmeldung an Weber		19-Mai-2015	1	19-Mai-2015	100%	1	1	0

	Sicherung von Anlagen auf Veräußerungsflächen der DB AG, Bruchköbel	[name]	25-Feb-2015	60	19-Mai-2015	100%	84	2	0
	Forderungsschreiben erledigt		19-Mai-2015	1	19-Mai-2015	100%	1	1	0
	Stellungnahme abgebeben	[name]	25-Feb-2015	1	25-Feb-2015	100%	1	1	0

	Wolfgang Kaserne, Hanau	[name]	12-Mai-2015	7	20-Mai-2015	67%	9	0	2
	In Plural NBG eingeben	[name]	20-Mai-2015	1	20-Mai-2015	0%	1	0	1
	Trassenplan an Häfner Öfner	[name]	18-Mai-2015	1	18-Mai-2015	100%	1	1	0
	Koordinierungsgespräch	[name]	12-Mai-2015	1	12-Mai-2015	100%	1	1	0

	Template Neu	[name]	20-Mai-2015	1	20-Mai-2015	0%	1	0	1
	neu		20-Mai-2015	1	20-Mai-2015	0%	1	0	1

	Kundenanfrage “Zum Goldacker 4”, Hanau
	Kalenderstart	[name]	05-Mai-2015	2	06-Mai-2015	0%	2	0	2
	neu		05-Mai-2015	2	06-Mai-2015	0%	2	0	2

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		01.01.14
		04.03.14
		18.04.14
		20.04.14
		25.04.14
		01.05.14
		10.06.14
		15.08.14
		08.12.14
		25.12.14